## Product Backlog
1 | <-- next available ID
ID | Importance | Story | Notes | How to demo | Size | Kyle Bittner | Noah | Blake | Allen | Sven | STATUS
| 1, 2, 3, 5, 8 |  |  |  | 1, 2, 3, 5, 8 | Team Member | Scrum Master | Product Manager | Team Member | Team Member
S3.0 | 3 | Cleaning up the UI desing | A final look for the app | N/A shown in app demo | 5 |  |  |  | Allen |  | x
S3.2 | 5 | Coffee shop pages | We need pages for each coffee shop with information, reviews, distance from user and pictures | (Insert name here ) will present this feature | 3 | [5 empty] | x
S3.3 | 1 | User Pages | We need user pages, basically same as the coffee shop pages but changed for users | (Insert name here ) will present this feature | 3 | [5 empty] | x
S3.5 | 2 | Push User Pages to final repo | User pages must be pushed to the main repo |  | 2 | [5 empty] | x
S7.1 | 2 | Wireless Network implementation | The user should only be able to access the wifi details when in close proximity to the shop. If there is no wifi information available, it should ask if there is a sign holding the information. If the answer is yes, it should open the camera. If not, return user to coffe-shop page. |  | 5 | [5 empty] | x

## Complete Stories
ID | Importance | Story | Notes | How to demo | Size | Kyle Bittner | Noah | Blake | Allen | Sven | STATUS
| 1, 2, 3, 5, 8 |  |  |  | 1, 2, 3, 5, 8 | Team Member | Scrum Master | Product Manager | Team Member | Team Member
S2.1 | 8 | Set up a Git Hub Repo for our main branch | The main branch will hold our final project | N/A shown in app demo | 3 |  | Noah |  |  |  | ✓
S2.2 | 8 | Set up a menu system for the app | A menu system as a graphical user interface to launch modules from, such as home, camera, coffee shops, ect. | UI will be shown throughout the app demo | 8 |  |  | Blake |  |  | ✓
S3.1 | 5 | Setting Coffee shop pages | We need a list of coffee shops in our app that can be clickable, with pictures, short descriptions and a rating system | (Insert name here ) will present this feature | 3 |  | Noah |  |  |  | ✓
S3.4 | 8 | Push coffee shop pages to final repo | Coffee shop pages must be pushed to the main repo |  | 2 |  | Noah | Blake |  |  | ✓
S4.3 | 8 | The app needs a camera screen so that we can implement text detectionto detect text | begin to create a camera module | mp4 video | 8 | Kyle |  |  |  |  | ✓
S4.2 | 8 | The app's camera screen will need to send an image to google's vision api to get a response, then print to user | implement google's cloud vision api into the camera module, text outputted to the user must be copy-able to the clipboard of the device | mp4 video | 5 | Kyle |  |  |  |  | ✓
S4.1 | 8 | Push Camera module to final repo | work on pushing the camera module to the main app | demo will be showing the camera module's features | 3 | Kyle |  | Blake |  |  | ✓
S5.1 | 8 | Complete the backlog for the app | We need a backlog for our app | N/A | 5 | Kyle | Noah | Blake | Allen | Sven | ✓
S6.1 | 8 | Create the presentation for the app | We need a power point presentation for the app | Will be the demo | 5 | Kyle | Noah | Blake | Allen | Sven | ✓